## Slide 1
PantriHub
Shared Inventory Platform for Food Banks
Project Scrum / Progress Check-in
March 18, 2026 | ENSE 281
Shivam Soni • Ethan Behl • Thomas Needham • Ishan Patel • Bushra Alkhateeb

## Slide 2
Meet the Team
Shivam Soni
Ethan Behl
Bushra Alkhateeb
Thomas Needham
Ishan Patel

## Slide 3
Agenda
01
Project Overview & Problem Statement
02
Current Sprint Status (Yellow)
03
What We Accomplished This Week
04
Technical Architecture & Demo
05
Next Week’s Plan & Recovery Strategy
06
Self-Reflection

## Slide 4
The Problem
Food banks in Saskatchewan operate in isolation
No visibility into each other’s inventory
Surplus at one location, shortages at another
Food waste from uncoordinated expiry tracking
Manual processes prone to error
PantriHub Solution
A shared dashboard that lets food banks see, search, and coordinate inventory across all locations in real time.
Validated through interviews with food banks in Regina, Calgary, and Vancouver

## Slide 5
Sprint Status
YELLOW
Why Yellow?
Team lead (Shivam) unavailable this week
All members had final round of midterms
Sprint 1 (Mar 10–16) behind schedule
Recovery Plan
Team sync to assign clear ownership
Compress Sprint 1 + overlap with Sprint 2
Regular check-ins to catch blockers early
Sprint 1: Auth + CRUD (FR-01–FR-07)
Mar 10–23 (extended)
Sprint 2: Dashboard + Search (FR-08–FR-14)
Mar 17–23 (overlapping)

## Slide 6
This Week’s Progress
Ishan & Bushra
Frontend
Sign Up & Registration page
(FR-01, FR-02)
HTML/Bootstrap layouts
Ethan
Backend
MongoDB database setup
Connection configuration
Thomas
Backend
Helping Ethan setting up the environment
Shivam
Team Lead / Flex
Unavailable last week
Resuming this week
Project scaffolding complete: Node.js/Express initialized with MVC folder structure

## Slide 7
MVC Architecture
Node.js / Express • MongoDB • HTML / CSS / Bootstrap • JavaScript • GitHub

## Slide 8
Work-in-Progress Demo
Project Structure
MVC folder organization (models/, views/, controllers/, routes/)
Complete
Sign Up / Registration Page
Frontend form with Bootstrap styling (FR-01, FR-02)
In Progress
Database Schema
MongoDB connection setup and initial schema design
In Progress
GitHub Repository
Version control, Kanban board, and documentation
Active
[LIVE DEMO HERE]

## Slide 9
Next Week’s Plan
1
Team Sync Meeting
Clearly assign task ownership, eliminate confusion
All
2
Auth Backend (FR-01–FR-03)
Login, registration, session management
Ethan + Thomas
3
Inventory CRUD (FR-04–FR-07)
Add, update, delete, mark availability
Ishan + Bushra
4
Shared Dashboard (FR-08–FR-10)
Cross-location inventory view, expiry alerts
Shivam (flex)
5
Regular Check-ins
Track progress, catch blockers early
All

## Slide 10
Self-Reflection
How did we feel?
Academic conflicts made this week stressful, but seeing the registration page come together was motivating. We wish we had more time to commit to development.
What are we proud of?
Despite limited availability, Ishan and Bushra delivered frontend work, and Ethan moved the database setup forward. The team kept going without Shivam being present.
What did we learn?
Clear task ownership matters. When the lead is absent and assignments are vague, progress slows. We also learned that academic schedules need to be factored into sprint planning.
Going forward?
We will build in buffer time for academic conflicts, hold structured check-ins, and make sure every task has a single owner before a sprint starts.

## Slide 11
Thank You
Questions?
github.com/bshra7/Inventory-Management-System-for-Food-Banks
PantriHub | ENSE 281 | March 2026